Role of Program for Results (P for R) Financing System in

Infrastructure Sector: Evidence from Egypt and Ethiopia

Ahmed M.Noureldin 1 and Doaa M. Salman Abdou* 2

1. Housing Building National Research center (HBRC), Cairo, Egypt

2. Department of Economics, October University for Modern Sciences and Arts (MSA), Giza, Egypt

Email address: dsalman@msa.eun.eg (D. M. S. Abdou)

*Corresponding author

Abstract: -

This study aim are two folds: first is to investigate the role of the World Bank funding via using a novel financing instrument called Program-for-Results (P for R) to strengthen the government programs. Secondly assessing the P for R program’s adopted in countries focusing on the directly effects and the results. The Bank Currently has three integral financing options to offer client countries: Investment Project Financing supports specific projects and disburses against specific expenditures and transactions; Development Policy Lending supports policy and institutional reforms and provides general budget support, and Program-for-Results financing supports government programs and disburses against results. Results for the P for R reflect on the new level because disbursements are directly linked to the achievement of measurable and verifiable outcome. As well, the Disbursement-Linked Indicators (DLIs) are used to provide governments with incentives to achieve critical program milestones and enhance the performance of programs. This study structured based on descriptive and observing the behavior of two countries government (Egypt and Ethiopia) for using of P for R financing loan in a national project. On ground the field of practices was the main indicator in this stage of the investigation, then one of P for R programs was compared to observe the effectiveness of this kind of financing system in this two countries specifically in the infrastructure sector, classifications of DLIs were the main parameter in this comparison. The outcome and the existing literature are analyzed to develop a multi-beneficial for country adopting P for R collaborative programs, as they should be applied to mitigate the same challenges and solve the institutional complications for the beneficial countries homogeneously. Furthermore, enhance the profit of this kind of program more than individually as a kind of sustainable management.

Keywords: Program for results (P for R), Foreign aid, International financial institutions, World Bank, results-based aid, and Disbursement-Linked-Indicators (DLIs)

- Introduction:

Researcher has identified three main criteria for the choice of the resource of finance in large‐scale projects; the size of the financial intermediary, experience in providing finance for projects of similar nature, and technical support this bank can offer with respect to the finance methods and financial planning [1]. In 2012, The World Bank’s created new Program for Results (PforR) instrument it is only the third financing instrument approved by its Board since the Bank was created in 1944. Although elements of results-based disbursement can be found in some previous operations, PforR is the first instrument designed to directly link disbursements to results. The development of the instrument was largely motivated by the need to fill a gap between investment (project) lending (IL) and development policy lending (DPL) to enable the Bank to support programs of service delivery [2]. Over the first two years, the volume of lending under PforR was restricted to not more than 5 percent of the sum of IBRD and IDA commitments. Following a review of the program at the 2-year mark, this was replaced by an indicative limit of 15 % of commitments, computed as an average over the three most recent years. The PforR program has expanded rapidly since its inception. As of March 1, 2016, 35 projects had been approved for a total commitment of $8.1 billion. It is too early to predict the long-term equilibrium share of PforR in the Bank’s portfolio, 1 but based on the initial response, it could be very substantial. Other MDBs, including the AfDB and the ADB, are also introducing results-based instruments so that the scope of the approach is extending beyond the World Bank.2 The Bank’s PforR-based lending already represents a sizeable sum compared with the resources under other results-based initiatives, some of which have been in existence for far longer.3 Besides its larger scale, the PforR program also generally demonstrates a more global mandate and broader sectoral focus than performance-based programs in other settings. It leverages differential country contributions, involves no upfront investment component, and operates on a loan basis only. Not all of the funding passing through these programs is disbursed strictly on the basis of results, including in the case of the PforR [3].

1 The $8.1 billion in total expected disbursements under the PforR represents about 3% of the World Bank's combined IBRD and IDA portfolio, which stood at $287 billion at the end of 2015.

2 As of March 2016, the ADB's portfolio of results-based lending comprised 8 operations with commitments totaling $1.8 billion.

3 For an overview of recent performance-based initiatives, see Perakis and Savedoff (2015). They include GPOBA (portfolio of $256 million), Salud Meso America (portfolio of $155 million, including $41 million from host governments), DFID-funded results-based programs for education (about $60 million) and parts of the large GAVI program (total resources over 2000-2015 $11.6 billion). Among the most prominent operations are performance-based payments for reducing deforestation, with over $3 billion committed as (potential) disbursements over a decade.

The PforR instrument meets the demand of client countries for financing and expertise to improve the performance and effectiveness of their own development programs. PforR operations disburse upon achievement of program results, provide support for the use of a government’s own systems, provide assurance that Bank financing is used appropriately, and ensure that the environmental and social impacts of the programs are adequately addressed. For each PforR operation, the Bank carries out a process of identification, preparation/ assessment, appraisal, and implementation support. The appraisal is informed by three assessments: a technical assessment (with a focus on strategic relevance and technical soundness of the program and its expenditure framework), a fiduciary assessment (with a focus on the procurement and financial management arrangements), and an environmental and social systems assessment (with a focus on the potential environmental and social impacts and risks). These assessments identify measures to enhance performance, build capacity, and mitigate risks, which are reflected in an integrated risk assessment and in the resulting Program Action Plan (PAP). Preparation also includes the identification of disbursement-linked indicators (DLIs), each with a verification protocol to ensure that a credible mechanism is in place to monitor and verify its achievement.

The PforR instrument is an increasingly important lending vehicle for the World Bank. Overall, the structure of the Bank’s assessments for the PforR’— technical, fiduciary, and environmental and social—has proven to be appropriate, and the assessments have generally been credible and comprehensive. The results frameworks, DLIs, and PAPs are often reasonably coherent, and risks related to PforR operations have generally been well identified and assessed. Nevertheless, there are areas in need of improvement when it comes to designing the programs to achieve results and to the monitoring and reporting systems. The PforR was envisioned to help focus more on results than other existing instruments, as well as to help strengthen country systems and induce further alignment/harmonization among donors. Because none of the PforR programs has yet closed, it is too early to draw definite conclusions about whether the instrument is doing a better job of achieving these objectives than alternative approaches. Nevertheless, some insights can be derived from the early design and implementation experience.

While the programs focus on results more explicitly than other instruments through the introduction of DLIs, these indicators are often-but not always-well integrated with the results frameworks. And while the results frameworks are often reasonably coherent, the program development objectives (PDOs) are rarely at the outcome level, and explanations of how the PforR objectives relate to the longer-term objectives of the supported government program are mostly absent from the program appraisal documents (PADs). To ensure a higher likelihood of achieving the ultimately desired developmental results, more consistent linking of the DLIs to the results frameworks and a clearer line of sight to the longer-term objectives of the program will be required.

The DLIs are designed with two main objectives: to be triggers for disbursements, with an inherent need for predictability, and to provide incentives for performance stretch targets.

In a number of cases, the DLIs are linked to relatively small shares of total program disbursements, or to routine and repetitive actions, rather than key activities necessary to achieve the PDOs, this point to an inherent tendency to shift the balance toward the disbursement objective. IEG finds that both ownership and partnership are well addressed in the Bank’s program documents, and the field visits found a considerable degree of government ownership of the programs under implementation. However, there is no evidence yet that the instrument has encouraged much additional financing by other donors, let alone any broader use of the strengthened country systems. Capacity building is an important part of the programs, but specific goals could have been defined more clearly in some cases, and the implementation of capacity building programs frequently has been delayed. Both the Bank teams and government counterparts have moved well up the learning curve for this new instrument, and countries have been eager to rely on their own financial management systems and procedures. So far, the Bank’s average costs for the preparation of new programs have been similar to those of other investment policy financing (IPF) operations, with significant variations among programs, while average Bank implementation costs have been significantly higher than for IPF operations. There may be increased positive externalities/public good aspects from strengthened country systems. Overall, however, there is not as yet sufficient evidence to derive any conclusions about the overall efficiency of PforR.

PforR operations, as described in the original Board paper (World Bank 2011a), are expected to do the following [4]:

- Finance and support borrowers' programs, which can be ongoing or new, sectoral or subsector, national or sub national, as well as community development programs.

- Disburse upon achievement of program results, as determined by the achievement of indicators that can be monitored and verified rather than disbursing for inputs. Advances of up to 25 %of outstanding commitments are allowed. Together with funds from other sources, Bank disbursements will finance a borrower's expenditure program rather than being linked to individual transactions.

- Provide support for the use of a government’s own systems to implement the program, including for financing planning, procurement, anti-corruption, and environmental and social standards.

- Provide assurance that Bank financing is used appropriately and that the environmental and social impacts of the programs are adequately addressed. To this end, the Bank will assess a program's fiduciary and environmental and social management systems and agree as necessary with a borrower on any additional measures to provide assurance those potential impacts to the environment and affected people are adequately addressed.

- Focus on strengthening the institutional capacity needed for programs to achieve their desired results, thereby enhancing development impact and sustainability. The strengthening of capacity to implement a program will be a priority area for both preparation and implementation support.

- Support improvements in governance and transparency by making program information publicly available and monitoring the achievement of results, including through enhancing the role of beneficiaries and civil society organizations.

- Help strengthens partnerships with governments and development partners, and increase efficiency by reducing transaction costs for the government and development partners. While the Board paper (World Bank 2011a) found it difficult to predict the budget implications for the Bank, experience with PforR features suggested that costs might be within the norm for IPF projects.

The theory of change of the PforR instrument is that PforR operations, working alongside the other two instruments, will enable the Bank to assist country clients in delivering priority results more efficiently by working through their own country systems, leveraging Bank financing with that of partners and other development organizations, and strengthening their own systems. The theory of change rests on three assumptions. The first is that working with country program systems will help strengthen them. This is a reasonable assumption for three reasons. First, sector ministries engage directly in the budget process and are less likely to work off budget because of their close relationships with donors. Second, donors have developed heightened concern about public financial management (PFM) and combating corruption, because of fiduciary concerns about their resources passing through national PFM systems, and because of the key role of these systems in linking policy and implementation. Third, it reduces transaction costs by avoiding multiple donor procedures and adopting the government standard.

A second assumption is that the costs of achieving the intended results have been accurately estimated and presented by the borrower and that the borrower can track these costs. This is important to provide reasonable assurance that program expenditures are used with due attention to the efficient use of resources. A third assumption is that it is possible to carry out technical, fiduciary, and environmental and social assessments, and in each case come to a clearly formulated, reliable conclusion. When systems are not adequate, they can be made so through targeted strengthening [4].

PforR operations focus on the behavioural and institutional changes that are required to realize this targeted strengthening, and in turn achieve results and manage associated risks. Hence it is expected that many will require some level of capacity-building activities, which will be informed by the technical, fiduciary, and environmental and social systems assessments. Capacity-building support, where needed, can be provided through different modalities, from direct technical assistance and training to specific actions or indicators that will strengthen performance. The PforR instrument is intended to complement, not replace, the Bank’s two existing lending instruments. While all Bank instruments focus on development results, borrowers are now able to choose from a wider range of instruments to suit their objectives, desired results, and risks. The description below, largely taken from the Board paper (World Bank 2011a), summarizes the differences and complementarities among the instruments (as per table 1) [4].

Table 1: complementary lending instruments

| Category | Project support lending (IPF) | Program-for-Results | Policy support lending (DPF) | Category |
| --- | --- | --- | --- | --- |
| Purpose | Supports specific investment operations | Supports government programs or subprograms | Supports policy and institutional actions | Purpose |
| Disbursement mechanism | Disburses against specific expenditures that support the operation | Disburses upon achievement of results and performance indicators | Disburses against policy and institutional actions | Disbursement mechanism |
| Implementation mechanisms | Bank IPF rules and procedures Funds for specific expenditures | Program systems Funds for specific expenditure program | Country policy processes Non-earmarked funds for general budget support | Implementation mechanisms |

Source: World Bank 2011a.

The Bank will determine the choice of lending instrument for specific countries, sectors, and programs in the context of its Country Partnership Framework and its assessment of the country’s policies, programs, and institutional capacity. PforR has the potential for significant development impacts, though it also has risks. For that reason, certain high-risk activities have been excluded from PforR operations: activities that pose a risk of potentially significant and irreversible adverse impacts on the environment or affected people (activities classified as Category A under IPF) and activities that involve procurement of works, goods, and services under contracts whose estimated value exceeds specified monetary amounts [2]. The following points describe the instrument approach:

- In PforR financing system operation, WB carries out a process of identification, preparation and assessment, appraisal, and implementation support.

- Appraisal of each operation is informed by assessments in three areas that are then applied to the overall program and its expenditures. The technical assessment focuses on the strategic relevance and technical soundness of the program and its expenditure framework, the results framework, and the Monitoring and evaluation (M&E) arrangements.

- The fiduciary assessment, covering the procurement and financial management arrangements, seeks to make sure that program funds are used appropriately. Both national and international competitive bidding systems are assessed.

- The environmental and social systems assessment seeks to make sure that the potential environmental and social impacts and risks are adequately addressed.  These assessments are expected to identify measures to enhance performance, build capacity, and mitigate key risks, and are reflected in an integrated risk assessment.

- The resulting Program Action Plan (PAP) is then reflected in the legal agreement between the Bank and the government. A central focus of preparation is the identification of disbursement-linked indicators (DLIs), each with a verification protocol to ensure that a credible mechanism is in place for monitoring and verifying its achievement. During implementation, the Bank task teams are expected to monitor overall program progress, associated expenditures, and the achievement of results (including the DLIs). Task teams monitor progress in implementing the PAP, changes in the program’s risks, and compliance with the provisions of the legal agreements.

- Technical support from the Bank team focuses on improving systems performance and resolving implementation issues.

- Operations are subject to the same corporate oversight functions as other Bank lending instruments, and the Bank retains the right to carry out investigations that it deems necessary and to sanction entities that are found to have engaged in fraud or corruption.

- The monitoring and verification of results is an essential feature of the instrument, and the DLIs require a credible verification process that is acceptable to the Bank and is agreed at the time of appraisal. The verification process may also include independent or Independent verification agency (IVA). DLIs are public information and their progress is supposed to be reported in the implementation reports. For transparency aspects, PforR documents are available to the public, giving stakeholders access to information about the performance of the public institutions and programs.

This evaluation provides early feedback on how the PforR instrument is working and its adherence to the stated objectives and intentions in the Board paper (World Bank 2011a). It has two objectives: (i) to assess the early experience with the design and implementation of PforR operations and (ii) to provide lessons and recommendations relevant for the use and possible improvement of this instrument. Since this is a new instrument, the evaluation has also paid significant attention to possible risks particularly the fiduciary, environmental, and social risks that have been in the forefront during discussions so far.

- Methods

  - Evaluation questions:

Any evaluation report for each PforR program should be included in the following question:

- What has been the overall experience to date with the design, preparation, and early implementation of PforR operations and the associated opportunities and challenges?

- What is the quality of the program assessments, including the technical, fiduciary systems, and environmental and social assessments?

- How effective has the PforR instrument (including policies, procedures, and guidelines, and their application) been in identifying, assessing, and mitigating critical risks?

- To what extent is the PforR instrument being used to strengthen national systems for financial management, procurement, environmental and social safeguards, and M&E?

  - Growth and Diversification of the PforR Portfolio:

WB’s PforR portfolio has grown rapidly. As of March 31, 2016, the Board had approved a total of 39 PforR operations, providing $9.5 billion of Bank financing to support a total of $49.9 billion in government programs AS shown in Table (2), with an additional 21 operations under preparation (having completed the concept stage), totaling $5.4 billion in expected Bank financing [5].

Table 2: IBRD/IDA Lending, Total and PforR operations, Fiscal 2012-16 (US $, billion)

| commitments | FY12 | FY13 | FY14 | FY15 | FY16a |
| --- | --- | --- | --- | --- | --- |
| P for R-IBRD lending | 0.3 | 0.1 | 0.5 | 0.9 | 3.3 |
| P for R-IDA lending | 0.1 | 0.7 | 1.2 | 1.3 | 1.1 |
| Total PforR-IBRD/IDA lending | 0.4 | 0.8 | 1.7 | 2.2 | 4.4 |
| IBRD lending | 20.4 | 14.8 | 18.2 | 23.1 | 23.6 |
| IDA lending | 14.3 | 16.2 | 21.3 | 18.4 | 6.8 |
| Total IBRD/IDA lending | 34.7 | 31.0 | 39.5 | 41.5 | 30.4 |
| Total PforR as percentage of total IBRD/IDA lending | 1.2 | 2.6 | 4.3 | 5.3 | 14.5 |

Source: business intelligence as April 28, 2016.

a. Commitment amount for fiscal 2016 is as of March 31, 2016.

As of March 31, 2016, all Bank Regions had at least two approved PforR operations (figure 1.A). The introduction of PforR to different Regions appears to be influenced by a range of factors. In Africa, for example, it has been influenced by the perspective that the PforR is a good instrument for supporting the regional agenda of building stronger institutions and delivering better services. In the Middle East and North Africa and East Asia and Pacific Regions, the instrument is regarded as a good fit for efforts to increase the emphasis on results and institutional capacity building. PforR operations cover most of the sectors in which the Bank traditionally provides financing. In terms of global practices (sectors), Water; Social, Urban, and Rural; and Health, Nutrition, and Population are the leading practices (figure 1. B) [2].

Egypt was ranked 118 out of 148 countries in terms of infrastructure (World Bank, 2015). Improvements in infrastructure are necessary to improve quality of life by 8 increasing access to basic services, create jobs, and encourage economic growth. The Government of Egypt plans to allocate EGP 135.4 Billion of the General State Budget for the fiscal year 2017/2018 for investments on its infrastructure [14].

Figure 1.A, 1. B: The PforR Portfolio (percentage of operations)

According to the above figure it can be note that the application of P for R financing system in Egypt is matching with the most two common practices that appalled by PforR (water and social, urban, rural &..), on the other hand, the need of PforR funding for water sector not considered one of the Ethiopian governmental priorities, it will appear clearly during this comparison study.

  - Classification of DLIs and Projects:

Following Table (3) outlines six types of DLIs. Classic investment operations typically finance the costs of the inputs required for a project and procured in a manner acceptable to the donor. The disbursement-linked indicators for such a project (denoted I in Table 3) will, therefore, be based on evidence of spending for example, on materials to repair bridges. Classic policy-based operations, on the other hand, are expected to have DLIs based on specific policy actions (denoted A in Table 3).In cases where the actions mandate a complex set of multiple measures to build institutions and improve the functioning of particular systems, the selected classification such as DLIs as SA, or system actions. Both A and SA DLIs are prescriptive in the sense that the actions of the borrower have to conform to detailed conditions agreed with the lender. The former will usually be more transparent than the latter because of the complexity of SA measures [6].

Turning to "results," the methodology distinguishes three DLIs. Output DLIs (O) involves the delivery of a specific product or service: for example, bridges constructed or repaired as in the case of the Nepal Bridges project. Outcome DLIs (OO) entail longer-term, broader achievements further down the results chain. Projects following the COD aid concept would rely only on these types of performance measures. Outcomes are conceptually preferable but may be difficult to calibrate and cost out, and are usually less subject to the direct control of those implementing the program supported by the project. They may, therefore, be more difficult to use as contractually acceptable DLIs. Moreover, while outputs and outcomes have a clear conceptual distinction – the first is a tangible good or service produced or delivered, while the second is an achievement that the paper focuses in it – in practice this can be less clear because it involves judgment on where the results chain starts and ends [7].

The third type of ‘result' DLI is a system output or SO, a measure of system performance or capability that does not necessarily reflect the delivery of the main outputs or outcomes that the system is intended to produce. SOs can be thought of as achievements that are further upstream than outputs but that may nevertheless be important in terms of signaling that the system is making progress towards effectiveness and sustainability. In Table 1, the example is capacity to process and complete bridge repairs on schedule. Unlike A and SA DLIs, the O, OO and also the SO DLIs are essentially “hands-off.” They specify the goals rather than the steps needed to attain it.

Table 3: DLI Classification

| DLI Type | Abbreviation | Example |
| --- | --- | --- |
| Input | I | Presentation of invoice for purchase of approved construction materials |
| Action | A | Preparation of Environmental and social Guide |
| System Action | SA | Implementation of an agreed program to strengthen the Management system |
| System Output | SO | Increased percentage of works completed per pre-agreed schedule |
| Output | O | Number of new constructions or rehabilitated with Allowance for the extent of repairs needed |
| Outcome | OO | Percent of secondary-school girls reaching agreed standard of achievement on standardized test |

Results-based projects can end their interventions at different points on the results chain. Some institution-building projects may disburse against SOs while others follow through to Os or even OOs. This complicates the classification of DLIs: if a particular system improvement is the development objective of the project does this mean that it should be consider as an output or even an outcome? In our view, doing so would debase these concepts which should relate to the provision of goods or services valued by project beneficiaries or even better measurable improvements in their well-being. In classifying the DLIs for the operations than it is considered as independently of the development objectives of the project. Table (4) includes details of all DLIs across all projects together with their classification.

The classification of DLIs according to whether a disbursement is scaled in proportion to performance (S) or is conditional on achieving a one-time threshold (T), an additional “scaled threshold” indicator captures DLIs that involve a staircase of progressively increasing hard thresholds each year. For example, Service Delivery project, the establishment of a monitoring system is a simple threshold, as a one-time accomplishment, is recognized by a one-time disbursement. Implementation of a water quality monitoring system is a scaled threshold, as the beneficiary must meet an annually increasing bar to receive payment. Disbursements for the percentage of households connected to the sewage systems are scaled to the level achieved.

- Results:

Results notes whether a clear baseline is spelled out for the DLI in the project document (Yes/No). In some cases, baselines may be implicit (Im): for example, when the DLI requires applying a policy or creating a program that clearly did not exist before the project, see Table (4). [2].

Table 4: List of the Egypt PforR Operations and DLIs Listed by Category

| Project Name |  | DLI Description |  | Type |  | Scale/ Threshold |  | Baseline |  | Value $ Mill. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Inclusive Housing Finance Program-for Results Project EGYPT |  | - Establishment and operation of an internal audit function within the Social Housing Fund (SHF) providing assurance service for the ownership and rental programs affiliated with the SHF |  | SA |  | T |  | Im |  | 25 |
|  |  | - Establishment and functioning of a housing monitoring and evaluation system and an M&E unit within SHF, and the preparation of the Multiyear Plan and Annual Targets informed by the M&E system |  | SA |  | T |  | Im |  | 25 |
|  |  | - Establishment and functioning of an accountability and transparency mechanism within SHF for implementing the Program |  | SA |  | T |  | Im |  | 50 |
|  |  | - Establishment by SHF of a functioning mechanism to monitor occupancy and vacancy of housing units by households receiving demand-side housing subsidy |  | SA |  | T |  | Im |  | 20 |
|  |  | - Percentage of ownership housing units occupied by low-income households after at least 1 year of receiving subsidies under the AMP |  | SO |  | S |  | Im |  | 30 |
|  |  | - Number of households receiving demand side homeownership subsidies for new housing units in each Fiscal Year during Program implementation under the Affordable Mortgage Program (AMP) |  | O |  | S |  | Y |  | 225 |
|  |  | - Number of new households participating in rental subsidy programs in each Fiscal Year during Program implementation |  | O |  | S |  | Y |  | 48.75 |
|  |  | - Percentage of demand-side subsidies provided supporting the purchase or rental of housing units located within a commute of 60 minutes or less to an employment centre |  | O |  | S |  | Y |  | 25 |
|  |  | - A number of demand-side subsidies provided supporting the purchase or rental of housing units developed by private sector entities in each Fiscal Year during Program implementation. (Private sector entities are those that are owned at least 51%by private individuals or are listed on the stock exchange) |  | O |  | S |  | Y |  | 50 |
|  | - Sustainable Rural Sanitation Services Program-for Results EGYPT |  | - Establishment and functioning of at least 167,000 new households (HH) connections to working sanitation systems in villages and satellites of which at least 10 percent of the connections are in satellites |  | O |  | T+S |  | Y | 220 |
|  |  |  | - Annual transfer of Performance-Based Capital Grants (PBGC) by the Ministry of Housing, Utilities and Urban Communities (MHUUC) to eligible WSCs |  | A |  | ST |  | Im | 40 |
|  |  |  | - Design and implementation of the Annual Performance Assessment (APA) system for the WSCs, and WSCs achievement of the required APA threshold scores in accordance with the Program Operations Manual |  | SA |  | T+S |  | Im | 170 |
|  |  |  | - Preparation and approval of new national tariff structure for water and sanitation services by MHUUC to allow for sustainable cost recovery |  | A |  | T |  | Im | 50 |
|  |  |  | - Establishment of Program Management Unit (PMU) and approval of a National Rural Sanitation Strategy by MHUU |  | A |  | T |  | Im | 50 |
|  |  |  | - Approval of Standard Operating Procedures for land acquisition under the National Rural Sanitation Program by MHUUC |  | A |  | T |  | Im | 18.625 |
|  | - Enhancing Shared Prosperity through Equitable Services ETHIOPIA |  | - Per capita increase in budgeted Federal Government block grant transfers to Regions, excluding Addis Ababa |  | A |  | T+S |  | Y | 90 |
|  |  |  | - Increased proportion of qualified female agricultural development agents (diploma level) |  | SO |  | T+S |  | Y | 30 |
|  |  |  | - Increased number of health extension workers who have graduated with a Level 4 qualification |  | SO |  | T+S |  | Y | 30 |
|  |  |  | - Increases in total number of students enrolled (net) in grades 5-8, in all Regions, excluding Addis Abab |  | O |  | T+S |  | Y | 60 |
|  |  |  | - Improved geographic equity in education and health service delivery outcomes, based on Net Enrollment Rate and Penta 3 Vaccine indicators for the bottom 10 percent of Performing Woreda |  | OO |  | T+S |  | Y | 60 |
|  |  |  | - Improved wealth equity in education and health service delivery outcomes, based on Net Attendance Rate and Penta 3 Vaccine indicators for the Bottom Wealth Quintile group |  | OO |  | T+S |  | Y | 30 |
|  |  |  | - Improved environmental and social management capacity at Woreda level |  | SA |  | T+S |  | Y | 50 |
|  |  |  | - Enhanced transparency and accountability through citizen engagement |  | SA |  | T+S |  | Y | 80 |
|  |  |  | - Establishment of a government system for benchmarking Woreda public financial management (“PFM”) performance (the “PFM Benchmarking Rating") |  | SA |  | T+S |  | Im | 42 |
|  |  |  | - Oversight functions of regional procurement regulatory bodies has been improved |  | SA |  | S |  | N | 20 |
|  |  |  | - Strengthened capacity of Woredas to effectively respond to fraud and corruption complaints |  | SA |  | S |  | Y | 30 |
|  |  |  | - Strengthened capacity of Woreda Council Finance and Budget Standing Committee members to provide effective oversight, transparency and accountability for budgets |  | SA |  | T+S |  | Y | 18 |
|  |  |  | - Improved development information and data for service delivery |  | SA |  | ST |  | N | 60 |

| - Second Urban Local Government Development Program - (ULGDP II) ETHIOPIA | Urban Local Governments (ULGs) have achieved Program minimum conditions as demonstrated in the Annual Performance Assessments (APA) | SA | S | Im | 90 |
| --- | --- | --- | --- | --- | --- |
|  | ULGs have strengthened institutional performance as demonstrated in the APA | SA | S | Im | 158 |
|  | ULGs have delivered infrastructure, maintenance, and supported job creation as per their capital investment plans and annual action plans, as demonstrated in the APA, and ensured that value for money is achieved | O | S | N | 75 |
|  | Regional government capacity building and support teams in place and support urban service delivery | SA | ST | Im | 13 |
|  | Offices of Regional Auditor Generals carry out timely audits of ULGs’ financial reports (by January 7 of each financial year). | A | S | Y | 7 |
|  | Regional environmental protection agencies timely review ULGs’ safeguards compliance. |  |  |  |  |
|  | Regional revenue authorities support ULGs’ efforts to generate revenue |  |  |  |  |
|  | The annual Ministry of Urban Development Housing and Construction capacity building activities for Program ULGs, regional governments, and the ministry complete |  |  |  |  |
|  | The APAs, independent procurement audits, and value for money audits are procured and completed on time |  |  |  |  |
| - Health Millennium Development Goals ETHIOPIA | - Deliveries attended by skilled birth providers (%) | O | S | Y | 20 |
|  | - Children 12-23 months immunized with Prevalent 3 vaccine (%) | O | S | Y | 19 |
|  | - Pregnant women receiving at least one antenatal care visit (%) | O | S | Y | 14.3 |
|  | - Contraceptive Prevalence Rate (%) | OO | S | Y | 20.5 |
|  | - Health Centers reporting HMIS data in time (Average number for 4 quarters) (%) | A | S | Y | 5 |
|  | - Development and implementation of Balanced Score Card approach to assess facility performance and related institutional incentives | SA | ST | Im | 20.2 |
|  | Development and implementation of Annual Rapid Facility Assessment to assess readiness to provide quality MNCH services | SA | ST | Im | 14 |
|  | Improved transparency of the Pharmaceutical Fund and Supply Agency (PFSA) procurement processes | SA | ST | Im | 7 |

- Discussion:

The following part provide comparison between SRSSP and ULGDP II, this assessment between the financial loan mechanism for Egyptian SRSSP and Ethiopian Second Urban Government development program (ULGDP II).  Throughout the following collected data base this paper looking forward to compare between the two P for R cases in Egypt and Ethiopia that look like similar in sector   according to global P for R kind of sectors (social, urban, rural), as follows:

- The behavior of disbursement and the financial mechanisms will be explained through the following tables for both case studs. Disbursement link indicators are the main key factor for this comparison.

- The development objective of the Egyptian case study “Sustainable Rural Sanitation Services Program for Results Project for Egypt” is to strengthen institutions and policies for increasing access and improving rural sanitation services in the Governorates of Beheira, Dakahliya, and Sharkiya in Egypt. The program activities are described through three key result areas: (1) improved sanitation access; (2) improved operational systems and practices of water and sanitation company (WSCs); and (3) strengthened national sector framework, and the scope of each results area. The strategy supported by the national rural sanitation program (NRSP) includes harnessing economies of scale by clustering villages to enhance the technical, economic, environmental, and social feasibility of wastewater treatment systems. The initial focus of the Government of Egypt (GoE) is to improve access and services in 769 villages in seven governorates that discharge untreated wastewater into the Al Salam Canal and the Rosetta Branch, which is estimated to require investments of about United States (U.S.) 2.8 billion dollars. The program is a results-based program supported by the World Bank aimed at strengthening institutions and systems to provide greater access and improved service delivery of rural sanitation services in three governorates in the Nile Delta [7],[8].

- The program builds on the government’s decision to shift from a centralized model of service delivery to a decentralized model that empowers the WSCs to improve service provision. The program focuses on the three WSCs operating respectively in the governorates of “Beheira”, “Dakahliya”, and “Sharkiya” respectively and helps to reduce poverty and enhance shared prosperity in these areas. The program will put in place a system of performance-based capital grant (PBCGs) from the Central Government to the WSCs to support priority rural sanitation investments identified [9]. The Program has made good progress after a slow start-up. As of early May 2018, approximately 92,000 HH connections have been designed; 15,000 HH connections are under construction; and 5,000 rural HH connections have been established (DLRs 1.1 & 1.2). This is complemented by the achievement of key sector reform initiatives: bi-annual transfers of performance-based grants from MHUUC to the WSCs (DLI2); preparation and approval of Performance Improvement Action Plans (PIAPs) for each of the WSCs (DLRs 3.1 & 3.2); preparation, approval, and the start of implementation of a new national tariff structure for water and sanitation services (DLI4); and approval of standard operating procedures (SOPs) for land acquisition under NRSP (DLI6). The PMU has also been established (DLR 5.1). Moreover, all due legal covenants and PAP actions under the Program have been fulfilled. The Program has completed the first cycle of verification and has disbursed US$ 78.625 against the first set of verified DLIs & DLRs. Another disbursement tranche of about US$76 million is expected after the second verification cycle is completed [10].

- The Ethiopian case study “Second Urban Government development program (ULGDP II) “will support the planning, delivery, and sustained provision of priority municipal services and infrastructure aims to address institutional and fiscal gaps at the urban local government (ULG) level [11]. The program development objective is to assist the Recipient in enhancing the institutional performance of participating urban local governments in developing and sustaining urban infrastructure and services. Phase one of the program focused on addressing the capacity and infrastructure deficits of 37 ULGs in total. This phase established a robust local government performance grant system, which has successfully delivered both institutional strengthening and associated infrastructure results in the limited number of cities within its scope.

- Overall, the ULGDP II is making good progress in improving capacity and urban management functions in the participating ULGs and had satisfactory progress towards achieving the development objectives. Four rounds of disbursements have been made so far and they were all above original estimates due to better-than-average performance by the cities. In total, US$312 million (or 92%) has been disbursed which is above the estimated projections. So far, an estimated 3 million urban residents, 50 percent female, are benefiting from improved infrastructure, and 293,397 jobs created of which 44% are for female. [12]. More specifically on the institutional front (DLI2), the average score of all 44 cities exceeded the design targets in all three years of the program and end of program target (80%) has been achieved in the third year of the program. The results include: (i) timely financial audits for 44 cities, with 13 cities having unqualified audits for EFY 2008 (2015/16)); (ii) improved revenue generation with 24 of the 44 cities increasing revenues by more than 10% (2016/17); and (iv) all 44 cities are routinely posting information publicly. 2. Results related to local infrastructure (DLI3) include: (i) about 714 km of urban cobblestone roads built or rehabilitated, (ii) about 509km of urban gravel roads built or rehabilitated, (iii) about 5479 hectares of serviced land for industry and MSEs delivered; and (iv) 119 hectares of public parks built [13].

Table 5: Disbursement-Linked Indicator Matrix for Egyptian case

| # | DLI | Bank financing allocated to the DLI | Of which Financing |  | Deadline for DLI Achievement1 | Minimum DLI value to be achieved to trigger disbursements of Bank Financing 2 | Maximum DLI value(s) expected to be achieved for Bank disbursements purposes 3 |  | Determination of Financing Amount to be disbursed against achieved and verified DLI value(s) 4 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | available for |  |  |  |  |  |  |
|  |  |  | Prior | Advances |  |  |  |  |  |
|  |  |  | results |  |  |  |  |  |  |
|  | Establishment and functioning of at least 167,000 new household (HH) connections to working sanitation systems in villages and satellites of which at least 10% of the connections are in satellites | US$220M | 0 | US$55M | June 2020 | This is a linearly scalable DLI for the new HH connections Y1 (2016): 25,000 | This is a linearly scalable DLI for the new HH Connections. Maximum for new HH connections is: US$192,050,000 Maximum for Final designs is: US$ 27,950,000 |  | Y1 (2016): US$15M on |
| 1 |  |  |  |  |  |  |  |  | final designs |
|  |  |  |  |  |  |  |  |  | Y2 (2017): US$12,950,000 |
|  |  |  |  |  |  |  |  |  | on final designs |
|  |  |  |  |  |  |  |  |  | Y2 (2017): US$1,150 per |
|  |  |  |  |  |  |  |  |  | new connection verified |
|  |  |  |  |  |  | Final designs Y2 (2017): 67,000 Final designs 2,000 connections (20% of 10,000)* Y3 (2018): 8,000 Connections (20% of 40,000)* Y4 (2019): 10,000 connections (20% of 50,000)* |  |  | Y3 (2018): US$1,150 per |
|  |  |  |  |  |  |  |  |  | new connection verified |
|  |  |  |  |  |  |  |  |  | Y4 (2019): US$1,150 per |
|  |  |  |  |  |  |  |  |  | new connection verified |
|  |  |  |  |  |  |  |  |  | Y5 (2020): US$1,150 per |
|  |  |  |  |  |  |  |  |  | new connection verified |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Y5 (2020): 13,400 Connections (20% of 67,000)* *Further, 10% of total connections made must be made in satellites |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Annual transfer of Performance Based Capital Grants (PBCGs) by MHUCC to eligible WSCs |  | US$40M |  |  |  | 0 |  |  | US$10M |  |  | June 2020 |  |  | N/A (not scalable) |  | N/A (not scalable) |  |  |  |  | US$8M per year when yearly results are achieved and verified |  |  |
| 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | DLI 3: Design and implementation of the Annual Performance Assessment (APA) system for the WSCs, and WSCs achievement of the required APA threshold scores in accordance with the Program Operations Manual |  | US$170M |  |  |  | 0 |  |  | US$42.5M |  |  | June 2020 |  |  | N/A (not scalable) |  | N/A (not scalable) |  |  |  |  | Y1 (2016): US$15M on Performance Improvement Action Plans prepared Y2 (2017): US$20M on APA Manual prepared and the first APA for each WSC carried out Y3 – Y5 (2018-2020): |  |  |
| 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | US$45M Each WSC |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | achieves the minimum |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | threshold APA scores |  |  |
|  |  |  |  | Preparation and approval of a new national tariff structure for water and sanitation services by MHUUC to allow for sustainable cost recovery |  | $50M |  |  |  | 10 |  |  | US$12.5 |  |  | June 2017 |  |  | N/A (not scalable) |  | N/A (not scalable) |  |  |  |  | Prior Result of New National Tariff Structure prepared: US$10M Y2 (2017): $40M New National Tariff Structure approved by MHUUC and decree issued |  |  |
| 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Establishment of PMU and approval of a National Rural Sanitation Strategy by MHUUC |  | $50M |  |  | 10 |  |  | US$12.5 |  |  | June 2020 |  |  |  | N/A (not scalable) |  | N/A (not scalable) |  |  |  |  | Prior Result of PMU created for the formulation and coordination of NRSP and the National rural Sanitation Strategy US$10M Y2 (2017): US$30M disbursed when National Rural Sanitation Strategy Approved by MHUUC. Y3 (2018) to Y5 (2020): US$10M disbursed with key action plans designed (not time-bound within Y3 and Y5) |  |  |  |
|  |  | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Approval of standard operating procedures for land acquisition under NRSP |  | $18.625M |  |  | 0 |  |  | US$5M |  |  | June 2017 |  |  |  | N/A (not scalable) |  | N/A (not scalable) |  |  |  |  | Y2 (2017): US$18.625M disbursed when Standard Operating procedures for land acquisition under NRSP prepared and approved |  |  |  |
|  |  | 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Table 6: Disbursement-Linked Indicator Matrix for Ethiopian case

|  |  | Total |  |  | As percent of |  |  | DLI Baseline |  |  |  |  |  | Indicative timeline for DLI achievement |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | financing |  |  | total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | allocated to |  |  | financing |  |  |  |  |  | Year 1 |  |  | Year 2 |  |  | Year 3 |  |  | Year 4 |  | Year 5 |  |  |
|  |  | DLI |  |  | amount |  |  |  |  |  | FY15 |  |  | FY16 |  |  | FY17 |  |  | FY18 |  | FY19 |  |  |
| DLI 1 ULGs have achieved Program minimum conditions in the annual assessment Allocated amount |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | 0 |  |  | 44 ULGs |  |  | 44 ULGs |  |  | 44 ULGs |  |  | 44 ULGs |  | 44 ULGs |  |  |
|  |  | $90 million |  |  | 23.68% |  |  |  |  |  | $18 million |  |  | $18 million |  |  | $18 million |  |  | $18 million |  | $18 million |  |  |
| DLI 2 ULGs have strengthened institutional performance as scored in the annual performance assessment Allocated amount |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | 60 (average |  |  | 65 (average |  |  | 70 (average |  |  | 75 (average |  | 80 (average |  |  |
|  |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | score) |  |  | score) |  |  | score) |  |  | score) |  | score) |  |  |
|  |  | $158 million |  |  | 41.58% |  |  |  |  |  | $21.8 |  |  | $34.1 million |  |  | $34.1 million |  |  | $34.1 million |  | $34.1million |  |  |
|  |  |  |  |  |  |  |  |  |  |  | million52 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DLI 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ULGs have delivered infrastructure, maintenance and supported job creation as per their annual action plans and the capital investment plans, as scored in the annual performance assessment, and ensured value for the money Allocated amount |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | 60 (average |  |  | 65 (average |  |  | 70 (average |  |  | 75 (average |  | 80 (average |  |  |
|  |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | score) |  |  | score) |  |  | score) |  |  | score) |  | score) |  |  |
|  |  | $75 million |  |  | 19.74% |  |  |  |  |  | $10.3 million |  |  | $16.2 million |  |  | $16.2 million |  |  | $16.2 million |  | $16.2 million |  |  |
| DLI 4 Regional government capacity building and support teams in place and support urban service delivery |  |  |  |  |  |  |  |  |  | Capacity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | building plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | of and terms |  |  |  |  |  | 80% in place |  |  | 80% in place |  |  | 80% in place |  |  |
|  |  |  |  |  |  |  |  |  |  | of reference |  |  | 80 in |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  | and 80 % |  |  | and 80 % |  |  | and 80 % |  |  |
|  |  |  |  |  |  |  |  |  |  | for regional |  |  | place%53 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | government |  |  |  |  |  | execution rate |  |  | execution rate |  |  | execution rate |  |  |
|  |  |  |  |  |  |  |  |  |  | teams are |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Place. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Allocated amount | $13 million |  |  | 3.42% |  |  |  |  |  | $2.6 million |  |  | $2.6 million |  |  | $2.6 million |  |  | $2.6 million |  |  | $2.6 million |  |  |
| DLI 5 ORAGs carry out ULG audits on time |  |  |  |  |  |  | 554 |  |  | 44 ULG |  |  | 44 ULG |  |  | 44 ULG |  |  | 44 ULG |  |  | 44 ULG |  |  |
|  |  |  |  |  |  |  |  |  |  | audits |  |  | audits |  |  | audits |  |  | audits |  |  | audits |  |  |
|  |  |  |  |  |  |  |  |  |  | completed |  |  | completed |  |  | completed |  |  | completed |  |  | completed |  |  |
| Allocated amount | $7 million |  |  | 1.84% |  |  |  |  |  | $1.4 million |  |  | $1.4 million |  |  | $1.4 million |  |  | $1.4 million |  |  | $1.4 million |  |  |
| DLI 6 |  |  |  |  |  |  |  |  |  |  |  |  | 44 ULG |  |  | 44 ULG |  |  | 44 ULG |  |  | 44 ULG |  |  |
| Regional environmental |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | safeguards |  |  | safeguards |  |  | safeguards |  |  | safeguards |  |  |
| protection agencies (REPA) |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | reviews/audits |  |  | reviews/audits |  |  | reviews/audits |  |  | reviews/audits |  |  |
| review of ULG safeguards |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | completed |  |  | completed |  |  | completed |  |  | completed |  |  |
| Compliance in a timely fashion. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Allocated amount | $6 million |  |  | 1.58% |  |  |  |  |  | $1.2 million |  |  | $1.2 million |  |  | $1.2 million |  |  | $1.2 million |  |  | $1.2 million |  |  |
| DLI 7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 44 ULG |  |  |  |  |  | 44 ULG |  |  |
| Regional revenue authority support ULG revenue mobilization |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  | revenue |  |  |  |  |  | revenue |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | mobilization |  |  |  |  |  | mobilization |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | supported |  |  |  |  |  | supported |  |  |
| Allocated amount | $4 million |  |  | 1.05% |  |  |  |  |  |  |  |  |  |  |  | $2.0 million |  |  |  |  |  | $2.0 million |  |  |
| DLI 8 |  |  |  |  |  |  |  |  |  | Compare- |  |  | Capacity |  |  | Capacity |  |  | Capacity |  |  | Capacity |  |  |
| Completion of annual MUDHCo capacity building activities for Program ULGs, regional governments and the ministry |  |  |  |  |  |  |  |  |  | hensive |  |  | building plan |  |  | building plan |  |  | building plan |  |  | building plan |  |  |
|  |  |  |  |  |  |  | 0 |  |  | annual |  |  | in place, 80% |  |  | in place, 80% |  |  | in place, 80% |  |  | in place, 80% |  |  |
|  |  |  |  |  |  |  |  |  |  | Program |  |  | of people in |  |  | of people in |  |  | of people in |  |  | of people in |  |  |
|  |  |  |  |  |  |  |  |  |  | capacity |  |  | place and |  |  | place and |  |  | place and |  |  | place and |  |  |
|  |  |  |  |  |  |  |  |  |  | building plan |  |  | minimum |  |  | minimum |  |  | minimum |  |  | minimum |  |  |
|  |  |  |  |  |  |  |  |  | in place and |  |  | 60% of the |  |  | 60% of the |  |  | 60% of the |  |  | 60% of the |  |  |  |
|  |  |  |  |  |  |  |  |  | terms of |  |  | plan |  |  | plan |  |  | plan |  |  | plan |  |  |  |
|  |  |  |  |  |  |  |  |  | reference |  |  | implemented |  |  | implemented |  |  | implemented |  |  | implemented |  |  |  |
|  |  |  |  |  |  |  |  |  | developed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Allocated amount | $22 million |  | 5.79% |  |  | 0 |  |  | $4.4 million |  |  | $4.4 million |  |  | $4.4 million |  |  | $4.4 million |  |  | $4.4 million |  |  |  |
| DLI 9 |  |  |  |  |  |  |  |  | APA |  |  | APA |  |  | APA and |  |  | APA and |  |  | APA and |  |  |  |
| Timely completion of Program annual performance assessments (APA) and value for money audits |  |  |  |  |  |  |  |  | completed on |  |  | completed on |  |  | value for |  |  | value for |  |  | value for |  |  |  |
|  |  |  |  |  |  | 0 |  |  | time |  |  | time |  |  | money |  |  | money |  |  | money |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | completed on |  |  | completed on |  |  | completed on |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | time |  |  | time |  |  | time |  |  |  |
| Allocated amount | US$5 million |  | 1.32% |  |  |  |  |  | $1 million |  |  | $1 million |  |  | $1 million |  |  | $1 million |  |  | $1 million |  |  |  |
| Total Financing Allocated: | US$380 |  | 100% |  |  | 0 |  |  | $60.7 million |  |  | $78.8 million |  |  | $80.8 million |  |  | $78.8 million |  |  | $80.8 million |  |  |  |
|  | million |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

- Conclusion:

The study showed that the rapid expansion of PforR operations is impressive considering that client governments still have the options of investment and policy loans and that PforR is financed from the existing pool of IDA and IBRD funds rather than creating additionally.  It is too soon to evaluate implementation experience in any systematic way, but the paper considers the possible implications of the instrument for the future role of the Bank, including in middle-income countries. This is an important question since many countries are expected to graduate out of IDA, assuming reasonably supportive global growth trends.

In the case of Ethiopia the P for R Projects number are more than Egyptian Projects while the application of PforR financing system in Egypt is matching with the most two common practices that appalled by P for R (water and social, urban, rural &..), on the other hand, the need of PforR funding for water sector not considered one of the Ethiopian governmental priorities, it appeared clearly during this comparison study.

Studying the application of PforR financing system in a collaborative program between Egypt and Ethiopia in Water resources practices is considered very useful for the two sides and a new challenge for P for R application especially the differentiation in rules, laws and regulation in both countries.0020This study provides insight for the future countries to take into consideration the given conditions to be consider in the future adopted projects.

References:

- [1] Turner, R., 2007. The financing of projects. The Wiley Guide to Project, Program, and Portfolio Management, 3, p.290.

- [2]“Working Paper 430 July 2016 - Center For Global” https://www.cgdev.org/sites/default/files/program-results-first-35 operations-working-paper430.pdf.

- [3] “An Early-Stage Assessment of the Process and Effects of a New Lending Instrument” http://ieg.worldbankgroup.org/sites/default/files/Data/Evaluation/files/program-for-results-full.pdf.

- [4] “World Bank 2011a” https://siteresources.worldbank.org/INTWDRS/Resources/WDR2011_Full_Text.pdf

- [5] Business Intelligence as of April 28, 2016, a. Commitment amount for fiscal 2016 is as of March 31, 2016.

- [6] “The Anatomy of Program-for-Results: An Approach to Results-Based Aid”, Alan Gelb and Nabil Hashmi

- https://www.cgdev.org/sites/default/files/anatomy-program-for-results.pdf

- [7] Cash on Delivery: A New Approach to Foreign Aid, (Birdsall and Savedoff), 2010.

- [8] “Sustainable Rural Sanitation Services Program-for Results (SRSSP)”, Program appraisal document, 2015.

- [9] Sustainable Rural Sanitation Services Program for Results (P154112), Implementation Status & Results Report: The World Bank, June 2018

- [10] Lessons Learned from Capacity-Building Support to the Egypt Sustainable Rural Sanitation Services Program for Results (PforR): Mohamed Fadel Ndaw,2017

- [11]Sustainable Rural Sanitation Services Program for Results (P154112), Implementation Status & Results Report: The World Bank, Public Disclosure Authorized, 5/ 2018

- [12] “Second Urban Government development program (ULGDP II) “, Program   appraisal document , 2014.

- [13] “Second Urban Government development program (ULGDP II) “, Implementation Status & Results Report, Public Disclosure Authorized, 21/6/2018.

- [14] Ministry of Finance, “Analytical Report on General State Budget for Fiscal year 2017/2018”. General State Budget. 2017

- http://www.mof.gov.eg/Arabic/%D8%B9%D9%86%D8%A7%D9%88%D9%8A%D9%86%20%D8%B1%D8%A6%D9%8A%D8%B3%D9%8A%D9%87/P E/Pages/budget17‐18.aspx